## Sheet1
EVALUATION ACTION PLAN
Partner Name: | Tearfund and RADO, CWS, CEEDF & MRC
Project Name: | Nepal Earthquake Appeal
Date of EAP: | 2017-03-01
Recommendation / Observation | Source | Team Judgement | Action Required | Action Owner | Due By | Progress | Comments
| Of the recommendation | Give explanation if not agreed in comments column | State what needs to be done to address the recommendation | Who is responsible for making it happen | When the action should be completed by
A common beneficiary selection approach should be developed across Partners, with closer attention paid (by MRC-N & RADO in particular) to involving the community in developing clear criteria on who is eligible for programmes, communicating this carefully to the wider community as well as involving the WCF and LDMC and ensuring that Community Mobilisers are fully engaged in the selection process. |  | Agreed | This action had partly started before the evaluation, and as described in the evaluation report significant progress had been made with beneficiary accountability systems. It is agreed however that beneficiary criteria should be clearer going forward and better explained and discussed with the intended beneficiaries, to further improve the transparency of the beneficiary selection process. As there are no new activities planned in the remaining period of the DEC project, no actions are required specifically for the DEC project but this learning will be taken on board for any future project activities in Nepal. | Nepal Response Manager | Ongoing for new project activities | Underway | This action will be ongoing for new project activities. Therefore, no due date is set.
The RADO handwashing station design should be reviewed and more careful consideration given to the siting of handwashing facilities in future. |  | Agreed | Recommendation will be taken on board for future actions. Some retrofitting and maintanance work will be done on existing hand washing facilities. | Nepal Response Manager | 2017-05-01 | Underway | The maintainance plan has been developed and RADO is working on maintainance.
RADO should consider returning to Bageshwori Secondary School to install a more conventional tippy tap design next to the latrine block |  | Agreed | Install additional tap system and maintain the existing one. | Nepal Response Manager | 2017-05-01 | Underway | RADO has developed a maintainance and WASH sector strengthening plan
Vocational training should continue and be reinforced, being careful to select the right participants and the right vocations, bearing in mind the particular needs and opportunities in each community. |  | Amended | Additional Vocational Training is not an activity for phase 2b but there are follow up activities to link those who have been trained with financial institutions and the enterprise promotion centre of the Government of Nepal. | Nepal Response Manager | 2016-12-01 | Completed | The follow up activites have been agreed with the partner and will continue during Phase 2b
RADO should reinforce their quality control systems and processes. |  | Agreed | RADO will update their quality control systems and processes and share them with the Head of Support Services at Tearfund. Tearfund will support the partner to reinforce the systems and procedures. | Nepal Response Manager | 2017-07-01 | Underway | Tearfund's Finance team and RADO management has agreed on the updated procedures for improving RADO's quality control.
KAP Surveys should be routinely conducted for all training events and ideally several months after the training, in order to capture evidence of the impact of trainings. |  | Agreed | Agreed that routinely KAP surveys should be conducted in the project area to capture evidence of impact such as knowledge on safe house construction, child protection etc. Tearfund recently conducted a survey on knowledge of safe building construction around the model houses and their impact, and will continue to conduct similar surveys for DRR, livelihoods, WASH while the project is ongoing. | Advisors on DRR, shelter and M&E officer | Till end of project, April 2018 | Not yet started
Community Mobilisers should be based within the communities they are serving in order to be most useful. |  | Agreed | Most Community Mobilisers are based already in the field, only those of RADO were not based there. After discussion with RADO, they have moved to be based in the VDCs they are working in for the last part of the project implementation. | Nepal Response Manager | 2017-05-01 | Completed | Community Mobilisers relocated in January 2017.
The focus of Phase 2b should be on the most affected and difficult to access wards, such as Agra Ward 7 and Tistung Ward 9 |  | Amended | Phase 2b activities are a continuation of those in 2a. As Tearfund is finishing Phase 2b activities by October 2017, no new activities are planned and it will be difficult to particularly target certain wards. However, for any future programming, we will take up the suggestion to focus on wards which have higher vulnerabilities. | Nepal Response Manager | 2017-05-01 | Underway
Tearfund should structure expectations with Partners about the end date of the programme as soon as practical in order that Partners can plan accordingly. |  | Agreed | Tearfund will agree with partners in writing the end date of the programme. A process is in place to phase out with partners. Tearfund recently followed a good process to phase out with partner CWS, including linking CWS with other potential donors, providing CWS staff with training in Project Cycle Managment and also staff leaving CWS with training on CV writing, interviews etc. This process will be repeated with the other partners. | Nepal Response Manager | Ongoing and will have phased exits (Partners and Projects) | Underway | A formal exit workshop has been agreed with CWS. Other partners are working on community exit and information to stakeholders at different levels
The primary relationship holder between Tearfund and the Partner should be made clear to Partners. |  | Amended | Meetings between Tearfund and the partners happen at various levels. Tearfund and partners have offices at the Palung field level and relationships between Tearfund and the partners are defined clearly there, with regular meetings happening. The other level of relationship is between Tearfund staff based in Kathmandu and the partner HQ in Hetauda. In the case of CWS, there is an added layer of communciation with the partner in Kathmandu as well, as they have an office there too. Tearfund agrees that going forward the outcome of meetings at the various levels should be better communicated internally. Tearfund will also encourage the partners to have better communication and more delegation from their HQ to field office. | Nepal Response Manager | Ongoing | Underway | This activity will be ongoing and progress will be recorded on a quarterly basis for the remaining time we work with these partners.
The monitoring framework should be agreed at the outset of a new programme and rolled out across all Managers and Partners. |  | Agreed | Will be agreed in future during project/programme design, shared and implemented by all managers and parters. | M&E officer with relevant staff | Completed | Completed | This will be actioned for new Tearfund programmes.. Tearfund as per it's country strategy 2016-2022, approved in October 2016, places a lot of emphasis on developing partner capacity in M&E.