## Sheet1
EVALUATION ACTION PLAN
Partner Name: |  | Tearfund and Medair
Project Name: |  | Typhoon Haiyan (Yolanda): An Evaluation of Tearfund's Phase 2 DEC Response
Recommendation / Observation | To be Addressed by | Source | Team Judgement | Action Required | Action Owner | Due By | Review Date | Progress | Comments
|  | Of the recommendation | Give explanation if not agreed in comments column | State what needs to be done to address the recommendation | Who is responsible for making it happen | When the action should be completed by | When the status of the action was last reviewed
1. Tearfund and Medair to update respective project workplans (all three locations) for the next five months. | Tearfund & Medair | On-site evaluation observation | Agreed | Revisit work schedules and targets; assess manpower and resources | Response Manager | 2015-06-01 | 2017-03-01 | Completed | Work schedules, targets & resources reviewed by Tearfund & Medair. All activities were completed by the end of the project period.
2. Conduct an immediate re-assessment on what the most vulnerable and poorest of the poor can practically achieve in applying retrofit kits already provided, but not yet installed. | Tearfund & Medair | On site observations | Agreed | Community surveys centred on affected households | Response Manager | 2015-06-01 | 2017-03-01 | Completed | Medair followed up with each SRK beneficiary and facilitated the completion. Beneficiary selection process for SRK was reviewed; additional 180 beneficiaries were selected
3. Intensify efforts to clarify the beneficiary criteria and selection process to community beneficiaries and LGUs. | Medair in particular | On site observations | Agreed | Well announced community and Barangay meetings for open communication and clarification | CD Medair | 2015-06-01 | 2017-03-01 | Completed | Medair followed up with community meetings and household visits to clarify. Medair shared the list of beneficiaries at the Barangay general assembly.
4. Re-allocate staff to ensure adequate coverage of needs arising from this evaluation. | Tearfund and Medair | Discussions with Terfund and Medair based on observations | Agreed | Identify where needs are highest in association with workplan rescheduling (recommendation 1) | CD Medair Response Manager-Tearfund | 2015-06-01 | 2017-03-01 | Completed | Tearfund's work plan was revisted, more staff were assigned for the livelihood intervention Medair- increased the number of carpenters to expedite the shelter construction process
5. Review terms and conditions of providing future retrofit kits to beneficiaries, some of whom may not be in a position to install them. | Medair and Tearfund | On site observations | Agreed | Internal review of past experience, matched with Recommendation 2 above | CD Medair Response Manager-Tearfund | 30 Sept 2015 | 2017-03-01 | Completed | Process reviewed. Medair followed up with each SRK beneficiary and facilitated the completion. ESA grant from the government also helped the beneficiaries to complete the retrofitting.
6. Reconsider the in-kind required from beneficiaries receiving houses in Cadiz, as this places additional pressure on peoples’ time. | Tearfund | Discussions with Tearfund based on observations | Agreed | Internal review of past experiences from Tearfund, with consideration of findings from Recommendation 2 above | Response Manager | 2015-06-01 | 2017-03-01 | Completed | The system in place was reviewed and changed. Beneficiaries who had provided in kind or labour support were compensated
7. Tearfund should provide one additional round of DRR capacity building to all Barangay Council members, in conjunction with the Municipal Disaster Risk Reduction Management Officers. | Tearfund | Discussions with beneficiariees and LGUs | Agreed | One additional round of capacity building, merging key elements of training into a simple, highly contextualised training session | Response Manager | 2015-06-01 | 2017-03-01 | Completed | Done
8. DRR measures should also once again be presented to project beneficiaries and the community as a whole, with specific attention given to relevant, and potentially multiple, disasters. | Tearfund & Medair | Discussions with beneficiariees and LGUs | Agreed | Repeat action 7 at community level, several times if possible to ensure broad coverage, but with information tailored to this level of audience | Response Manager | 2015-06-01 | 2017-03-01 | Completed | Done
9. Livelihood support should begin immediately in SHIELD, based on defined criteria for selection and management. Cash transfers should be prioritised. | Tearfund | Field observations and verification with intended beneficiaries | Agreed | Immediate launch of intended livelihood activities, with full back-stopping support by Tearfund and implicated partners | Response Manager | 2015-06-01 | 2017-03-01 | Completed | Cash for livelihoods support through cash transfer given to the planned 2,000 beneficiaries
10. If the SHIELD budget allows, priority attention should be given to identifying and supporting immediate livelihood support to relocated households – men and women. | Tearfund | Needs identified through FGDs and KIIS | Agreed | Identify possible livelihood activities if resources can be identified following Recommendation 1, back-stopping support provided, based on a rapid assessment of affected peoples' prioirty needs | Response Manager | 2015-06-01 | 2017-03-01 | Completed | It was not possible to include this within the SHIELD budget. However, the team advocated with Local Governemnet Unit to provide livelihood opportunities for the relocated families
11. Livelihoods involving livestock should be given priority to supporting breeding programmes, which may require additional technical training for those beneficiaries. | Tearfund | Discussions with Tearfund staff and Evaluation team | Agreed | Initiate small-scall livestock livelihood support porjects. | Response Manager | 2015-06-01 | 2017-03-01 | Completed | Done.
12. Identify possible (supplementary) means to introduce basic livelihood support to communities in Leyte, perhaps through budget re-adjustment. | Medair, with Tearfund | Needs identified on the ground through FGDs and KIIS | Agreed | Identify, on the basis of already available information, potential livelihood activities that might be supported at least with some sectors of the most vulnerable communities | Response Manager | 30 Sept 2015 | 2017-03-01 | Completed | Done New livelihood project in the Medair operation area has been started by FH Philippines with the support of Tearfund.
13. Prior to exiting, ensure that each Municipality and participating government agency has an up-to-date list of project beneficiaries from Tearfund/Medair (with all sensitive data removed), | Tearfund & Medair | Needs raised through meetings with government partners re specific activities relating to livelihoods | Agreed | Data preparation and explanation prior to handover and exit, with sensitive data removed | Response Manager-Tearfund CD Medair | 2015-10-31 | 2017-03-01 | Completed | Beneficiary list shared with LGUs in both Medair and Tearfund operation area
14. Promotion of good hygiene practices should be broader than current outreach, especially for children. | Tearfund | Direct observations on the ground | Agreed | Additonal awareness raising subject to additional funding being secured or made available from within the existing budget | CD Medair Response Manager-Tearfund | 2015-06-01 | 2017-03-01 | Completed | Medair provided latrine facility to core shelter benefciaries under its WaSH project. Tearfund- second round of hygiene promotion orientation was done at community level