## Home page
3.3.3 Light Wheel survey planning workbook
This workbook has different tools to help you keep track of all your survey planning decisions and make sure everyone involved in administering the survey is well informed. It includes:
Tab 1a, 1b & 1c: Tools for selecting participants for your random sample
Tab 2: A budget template to help you think through the costs of running a survey
Tab 3: A framework for documenting key data-collection planning decisions
Tab 4: A template Gantt chart to map out when each stage of the survey will happen and how long it will take
Tab 5: A daily survey schedule to organise who will be interviewed, when and by whom

## 1a Sample size
Sampling tool – sample size
For more information on sampling and how to create a representative sample, refer to 'The Light Wheel survey', Section 2.3 in the Light Wheel toolkit (see learn.tearfund.org/LW2)
https://www.calculator.net/sample-size-calculator.html
Use the sample-size calculator above (or use Google to search for one) Enter in your exact population size. Choose a 95 per cent confidence level. Enter your confidence interval of 5 or 7 or 10 per cent. If the sample-size calculator asks you to enter a population proportion, you can enter 50 per cent. Press ‘calculate’ and the calculator will tell you how many people you need to interview!
Example based on 500 people
Population size = 500 people | 95% ± 5% | 95% ± 7% | 95% ± 10%
1. Calculate sample size (from link) | 218 | 142 | 81
2. Calculate 15% of non-responders | 32.7 | 21.3 | 12.15
3. Add sample size plus 15% | 250.7 | 163.3 | 93.15
4. Final sample size | 251 | 163 | 93
Population size = XXX people | 95% ± 5% | 95% ± 7% | 95% ± 10%
1. Calculate sample size (from link)
2. Calculate 15% of non-responders | 0 | 0 | 0
3. Add sample size plus 15% | 0 | 0 | 0
4. Final sample size | 0 | 0 | 0
Working across multiple sites
If you are working across multiple churches or project locations, add up all the people you want to evaluate from all locations into one total population size. For example, your population size could be calculated in a table like the one below.
Calculate what percentage of the total population each location represents. To do this, divide the population size for each location by the total population and multiply the result by 100 to get a percentage. For example:
| Population size | % of total | Number to interview at each location
Church 1 | 250 | 17.17% | 62.8434
Church 2 | 52 | 3.571% | 13.0714
Church 3 | 89 | 6.113% | 22.3723
Church 4 | 180 | 12.36% | 45.2473
Church 5 | 35 | 2.404% | 8.7981
Church 6 | 350 | 24.04% | 87.9808
Church 7 | 120 | 8.242% | 30.1648
Church 8 | 76 | 5.22% | 19.1044
Church 9 | 50 | 3.434% | 12.5687
Church 10 | 190 | 13.05% | 47.761
Church 11 | 64 | 4.396% | 16.0879
Population size = | 1456
95% +/- 5% Sample size = | 305
20% not available = | 61
Total to interview = | 366
The next step is to create a random list of all of the people you will interview in your sample. Use 'Sampling tool 1b (create a random list)' to generate this for you.
Note on B3: HELEN to add hyperlink to Part 2 page on Tearfund Learn: learn.tearfund.org/LW2 Please also note that during the toolkit proofread, I noticed a mismatch between the section number and name given here and what is actually in the toolkit. So I've changed the text here to 'The Light Wheel survey', Section 2.3 -Sarah La Trobe learn.tearfund.org/LW5 -Sara Baines

## 1b Create random list
Sampling tool – create a random list
The first step in creating your randomised sample to interview is to create a master list showing the names of every single person in your population.
This list can be digital (eg in Excel or Google Sheets) or it can be on paper. For example, if you have ‘sign-in’ sheets at all of your activities, you can use these as your ‘list’. Or, for example, if your ‘list’ is on WhatsApp or your phone, it might be best to transfer everyone’s name into a digital Google Sheet, or write the names onto paper. Please follow good data storage protocols to keep participant data confidential.
This template uses a random-number-generating formula to randomly select names from your spreadsheet list to interview. Paste all names in your population list into the yellow boxes below. Tell the sheet how many names you need to randomly select, in the blue box, and it will generate a list of names for you!
Step 1️⃣: Determine your population size.
Where you are running a survey across multiple locations, each location needs to compile the list of participants (the entire population) into their own list. For example:
Location name | Population size | List
Church 1 | 250 | Create a paper or digital list of all 250 names
Church 2 | 52 | Create a paper or digital list of all 52 names
Church 3 | 89 | Create a paper or digital list of all 89 names
Church 4 | 180 | Create a paper or digital list of all 180 names
Church 5 | 35 | Create a paper or digital list of all 35 names
Total population = | 606
Step 2️⃣: Determine your sample size (explained in Tab 1a).
Population size = 606 people |  | 95% ± 5%
1. Calculate sample size (from link) |  | 236 |  | On the next page 'Sampling tool 1c (final interview list)', you will paste the generated list of people (from column E) to interview in your survey.
2. Calculate 15% of non-responders |  | 35.4
3. Add sample size plus 15% |  | 271.4
4. Final sample size |  | 271
Step 3️⃣: Generate a random list of names to interview.
| Enter the full list of 606 names here.⬇️ |  |  | Enter the number for sample size in blue box (271).⬇️
Random number | Name |  | How many names? | 271
0.95476 | Arthur Mitchell |  |  | Sienna Sun
0.39789 | Brooke Garcia |  |  | Kobie Laws
0.30227 | Andrew Perry |  |  | Kenneth Stein
0.58003 | Jessica Cuevas |  |  | Katlynn Daly
0.69331 | Ariana Love |  |  | Johan Alves
0.33963 | Michelle Hayes |  |  | Keara Clifton
0.80648 | Donald Holmes |  |  | Aubrie Atkins
0.078679 | Christopher Adams |  |  | Devyn Sikes
0.041665 | Anthony Dudley |  |  | Mariah Shoemaker
0.52495 | Jason Cook |  |  | Karla Baum
0.86529 | Michael Frazier |  |  | Triniti Dickey
0.82215 | Jason Johnson |  |  | Michael Johnson MD
0.77151 | Carlos Perez |  |  | Sasha Cunningham
0.16604 | Michael Evans |  |  | Kaitlyn Herron
0.87032 | Alexandria Taylor |  |  | Courtney Reid
0.80455 | Jamie Morrison |  |  | Treyton Mcnutt
0.0071592 | Christian Brown |  |  | Marina Dobbins
0.85954 | Matthew Briggs |  |  | Tayla Coronado
0.38797 | Kevin Smith |  |  | Antoine McCauley
0.80535 | Mr. Kyle Dougherty |  |  | Howard Zhang
0.2179 | Brent Wheeler |  |  | Dyllan Ayers
0.73745 | Ms. Elizabeth Kim |  |  | Cale Mosier
0.31258 | Nicole Davis |  |  | Alexandria Taylor
0.99804 | Jeffrey Wiggins |  |  | Ivonne Rees
0.87342 | Kyle Lane |  |  | Tammy Goodwin
0.41441 | David Garcia |  |  | Draven Keefer
0.64538 | Tyler Brown |  |  | Michelle Hayes
0.15163 | Paula Taylor |  |  | Angela Cook
0.091483 | Elizabeth Torres |  |  | Kaylynn Burroughs
0.86383 | Lisa George |  |  | Joy Kunz
0.19623 | Anna Kennedy |  |  | Nicole Davis
0.59051 | Sean Roberts |  |  | Brianne Danner
0.14451 | Jean Chung |  |  | Karlie Bernal
0.35696 | Mr. Kevin Nelson |  |  | Korey Moffitt
0.94892 | Cindy Carter |  |  | Kami Gaffney
0.87097 | Tyler Smith |  |  | Annabel Winkler
0.034501 | Tammy Goodwin |  |  | Emily Miller MD
0.99082 | Michael Johnson MD |  |  | Emanuel Colby
0.64902 | Brenda Martin |  |  | Patience Edmondson
0.94653 | Cynthia Flores |  |  | Michael Evans
0.81186 | Darlene Davis |  |  | Rachel Waldrop
0.16108 | Donald Ward |  |  | Ashlin Lozano
0.51984 | Courtney Reid |  |  | Cynthia Houston
0.53864 | Ian Kim |  |  | Katrina Bragg
0.47574 | Larry Terrell |  |  | Sammy Stewart
0.3208 | Breanna Flores |  |  | Shira Salcido
0.5267 | Eric Wilson DDS |  |  | Jaron Horton
0.13735 | Seth Coleman |  |  | Alejandro Henson
0.74182 | Stephen Merritt |  |  | Heather Huffman
0.7398 | Mark Glass |  |  | Jevon Weller
0.55603 | Evelyn Watson |  |  | Lesly Mackey
0.27056 | Andrea Carter |  |  | Dyllan Page
0.31696 | Austin Mullen |  |  | Daryl Tirado
0.73802 | Christina Cabrera |  |  | Talon Gray
0.92629 | Cynthia Houston |  |  | Christina Maldonado
0.59707 | Paula Adams |  |  | Reid Lance
0.67899 | Corey Allen |  |  | Melinda Metz
0.90424 | Robert Buck |  |  | Garret Engel
0.60167 | Angela Cook |  |  | Rhett Neumann
0.23339 | David Perez |  |  | Elena Irby
0.84772 | Nicholas Campbell |  |  | Cindy Harrison
0.62755 | Lisa Davis |  |  | Angel Nolan
0.41469 | Deanna Graves |  |  | Josue Barnett
0.4608 | Heather Alexander |  |  | Cynthia Flores
0.21794 | Veronica Mora |  |  | Jessica Pugh
0.21424 | Amy Barnes |  |  | Cordell Temple
0.6605 | Nicholas Santiago |  |  | Kristopher Hutcheson
0.5224 | Emily Miller MD |  |  | Briana Rossi
0.80991 | Heather Boyer |  |  | Daryl Canady
0.27289 | Heather Huffman |  |  | Kyle Lane
0.086896 | Kenneth Stein |  |  | Marian Hedges
0.98471 | Michael Weber |  |  | Slade Mock
0.071788 | John Wilson |  |  | Ivan Herron
0.57646 | Robert Romero |  |  | Quinton Miner
0.76707 | Brooke Montgomery MD |  |  | Alea Hubert
0.78385 | Sylvia Garcia |  |  | Maximiliano Childress
0.34576 | Jamie Ellison |  |  | Ellis Downing
0.15396 | Katie Elliott |  |  | Trey Dominguez
0.41256 | Katie Braun |  |  | Alton Sales
0.54822 | Rachel Hebert |  |  | Alberto Alonso
0.85004 | Dennis Wilson |  |  | Galilea Ha
0.48026 | Patrick Jefferson |  |  | Braydon Lemke
0.82148 | Mary James |  |  | Notnamed Blue
0.16468 | Deborah Campos |  |  | Theo Wiese
0.48014 | Gregory Smith |  |  | Vernon Pulido
0.12944 | Ashley Jennings |  |  | Rhys Wharton
0.77063 | Donald Mcintyre |  |  | Cedrick Elam
0.5347 | Cindy Harrison |  |  | Taylor Griggs
0.67095 | John Cohen |  |  | Lisa George
0.74847 | Ryan Henry |  |  | Hasan Webber
0.39518 | William Bennett |  |  | Christina Cabrera
0.95279 | Michael Cole |  |  | Grayson Yazzie
0.70242 | Mark Lawrence |  |  | Arthur Mitchell
0.049485 | Ashley Hall |  |  | Erich Lindquist
0.40257 | Michael Cruz |  |  | Brent Wheeler
0.83114 | Madison Walker |  |  | Donald Ward
0.21193 | Jessica Pugh |  |  | Barry Ricker
0.98386 | Ivonne Wirth |  |  | Arnold Chen
0.93016 | Aidan Eubanks |  |  | Caylin Way
0.55962 | Patience Roach |  |  | Camryn Pimentel
0.3554 | Felix Lyles |  |  | Lukas Littleton
0.46773 | India Thomas |  |  | Princess Cummins
0.57895 | Shaina McCann |  |  | Hillary Merritt
0.21899 | Devyn Sikes |  |  | Darrian Joyce
0.85762 | Ashlin Lozano |  |  | Daijah Quezada
0.0098919 | Notnamed Gipson |  |  | Quinn Goldstein
0.25806 | Ross New |  |  | Charity Bowers
0.15549 | Camille Singleton |  |  | Deon Knoll
0.81461 | Annemarie Page |  |  | Riley Headley
0.9469 | Courtney Rose |  |  | Deion Pate
0.20689 | Cassie Bittner |  |  | Patrick Jefferson
0.33384 | Antoine McCauley |  |  | Jerrod Patten
0.55034 | Chase Gage |  |  | Quentin Bernier
0.017938 | Claire Herron |  |  | Sincere Finley
0.38251 | Talon Gray |  |  | Kelis Gall
0.42712 | Micah Paulsen |  |  | Tavian Yazzie
0.29869 | Shira Salcido |  |  | Francisco Bone
0.73817 | Carleigh Marcus |  |  | Kahlil Fink
0.053755 | Sunny Agee |  |  | Jaime Doyle
0.46025 | Brynn Washington |  |  | Jakob Thornton
0.27776 | Sincere Finley |  |  | Brenda Martin
0.76992 | Keegan Vickers |  |  | Francis Centeno
0.80423 | Jamison Hilliard |  |  | Luc Field
0.72691 | Jorden Cantrell |  |  | Cale Felder
0.86087 | Liam Oates |  |  | Blaise Leary
0.34147 | Korey Moffitt |  |  | Duane Kelly
0.70864 | Broderick Mathews |  |  | Joshua Malley
0.16369 | Barry Ricker |  |  | Tonya Slade
0.53982 | Kain Odell |  |  | Katheryn Salvador
0.88135 | Tayla Coronado |  |  | Notnamed Gipson
0.36249 | Zaire Landers |  |  | Reed Viera
0.93446 | Raekwon McLean |  |  | Lina Lorenzo
0.36129 | Bonnie Montes |  |  | Sylvia Garcia
0.88477 | Julian Murry |  |  | David Garcia
0.17528 | Ciara Sutter |  |  | Simeon Hicks
0.77626 | Jaylen McCullough |  |  | Asa Winn
0.10076 | Kimberlee Mitchell |  |  | Cedric McClendon
0.36005 | Cecelia Hennessy |  |  | Paola Hunt
0.56852 | Lloyd York |  |  | Harrison Hennessy
0.92381 | Ismael Nielson |  |  | Abby Branch
0.50895 | Reilly Kinney |  |  | Kathrine Root
0.45999 | Luke Carrier |  |  | Janet Ali
0.51671 | Francis Centeno |  |  | Jaylin Wiseman
0.32099 | Humberto Ogden |  |  | Jaylene Duffy
0.46107 | Dane James |  |  | Pamela Aquino
0.81528 | Trey Jerome |  |  | Aman Lester
0.69689 | Laila Stump |  |  | Dillon Justice
0.078702 | Leo Desantis |  |  | Linnea Weis
0.60981 | Jaime Doyle |  |  | Korbin Ricks
0.80314 | Yaritza Tobin |  |  | Cailey Rubio
0.36361 | Jaret Wenger |  |  | Diamond Stump
0.98749 | Ellis Downing |  |  | Cecelia Luce
0.91816 | Kayden McClendon |  |  | Paula Taylor
0.63363 | Joseluis Flanders |  |  | Deasia Keane
0.29548 | Theo Wiese |  |  | Chase Montes
0.43295 | Essence Kiefer |  |  | Santino Delgadillo
0.74679 | Mason Basham |  |  | Jamia Jefferson
0.94715 | Craig Dion |  |  | Troy Voss
0.93593 | Ayla Petrie |  |  | Trinity Paredes
0.16023 | Kory Davis |  |  | Trista Schaeffer
0.52764 | Marcellus Halstead |  |  | Jaydon Ray
0.7568 | Donovan Fleming |  |  | Alyssa Rocha
0.43887 | Corina Clarkson |  |  | Jania Brinson
0.92273 | Jaquez Kay |  |  | Mason Basham
0.48253 | Kaylynn Burroughs |  |  | Daja Helms
0.36219 | Bryanna Gentile |  |  | Aryanna Longo
0.23109 | Sienna Sun |  |  | Delanie Wise
0.83748 | Cedric McClendon |  |  | Ulises Rapp
0.73805 | Beatrice Christiansen |  |  | Kimberlee Mitchell
0.54187 | Jalen Quick |  |  | Devan Hamilton
0.4285 | Garett Crawley |  |  | Fernando Peebles
0.32361 | Alesha Freedman |  |  | Felix Lyles
0.83619 | Harley Briggs |  |  | Rochelle Early
0.28742 | Tyreese Fullerton |  |  | Hunter Lerma
0.23669 | Cayden Kelsey |  |  | Corina Clarkson
0.64961 | Santino Delgadillo |  |  | Jeffrey Wiggins
0.71234 | Cedrick Elam |  |  | Keven Conner
0.078325 | Will Goodrich |  |  | Dwayne Henley
0.359 | Kaylah Christian |  |  | Jaycie Pak
0.51244 | Coleton Zielinski |  |  | Jean Chung
0.11078 | Zackary Poindexter |  |  | Vincent Pyle
0.39239 | Sidney Franklin |  |  | Chauncey Hollis
0.47968 | Leona Childress |  |  | Brynn Washington
0.27024 | Madison Schumacher |  |  | Julieta Herzog
0.59418 | Cale Felder |  |  | Keegan Vickers
0.15271 | Erich Delagarza |  |  | Breanna Flores
0.44303 | Duane Kelly |  |  | Jaylen McCullough
0.63407 | Janay Almeida |  |  | Kamryn Aragon
0.12029 | Chase Devlin |  |  | Mercedes Bullard
0.59669 | Lesly Mackey |  |  | Stephen Merritt
0.77413 | Kory Quiroz |  |  | Rachel Coulter
0.61966 | Tabitha Yarbrough |  |  | Paula Adams
0.084909 | Jamir Mayhew |  |  | Robert Romero
0.11808 | Reginald Pierson |  |  | Giancarlo Kilgore
0.068591 | Guadalupe Kurtz |  |  | Danica Murillo
0.50634 | Gavyn Ridgeway |  |  | Ryan Henry
0.35129 | Trey Dominguez |  |  | Edna Wisniewski
0.8369 | Ervin Moriarty |  |  | Justice McCrary
0.8027 | Margo Mueller |  |  | Ananda Villegas
0.15783 | Charity Bowers |  |  | Claire Herron
0.69358 | Danika Espinoza |  |  | Morgan Dupont
0.42633 | Keyshawn Kirkpatrick |  |  | Enoch Burgess
0.675 | Cristofer DeJesus |  |  | Malika Medina
0.42932 | Caley Galindo |  |  | Katie Elliott
0.061531 | Princess Cummins |  |  | Cristopher Dube
0.48145 | Juliann Dobbs |  |  | Jack London
0.39418 | Tristen Suarez |  |  | Sydney Madrigal
0.36042 | Rachel Waldrop |  |  | Agustin Webster
0.6082 | Danica Murillo |  |  | Milena Neil
0.43769 | Madison Mchenry |  |  | Brooke Garcia
0.54345 | Harris Harley |  |  | Daisha Pagano
0.802 | Dwight Daily |  |  | Shakayla Russ
0.99286 | Courtney Seeley |  |  | Reginald Sears
0.31853 | Kobie Laws |  |  | Cade Denny
0.569 | Octavio Riggins |  |  | Kevin Smith
0.75677 | Madelyn Jung |  |  | Jameson Brackett
0.16484 | Dorien Armenta |  |  | Jessie Samuels
0.79867 | Carlo Hodgson |  |  | Kayden McClendon
0.84853 | Michaela Duenas |  |  | Seth Coleman
0.35522 | Tavian Yazzie |  |  | Dorien Armenta
0.46732 | Stevie Sutherland |  |  | Courtney Rose
0.74206 | Joy Fernandes |  |  | Ariana Love
0.66449 | Bailey Cordero |  |  | Cristofer DeJesus
0.99642 | Devlin Waugh |  |  | Deon Abel
0.77589 | Zechariah Gough |  |  | Ty Hauser
0.045881 | Emanuel Colby |  |  | Susana Crider
0.77111 | Emilee Boyle |  |  | Analise McIntosh
0.67721 | Hamza Yates |  |  | Zaire Merchant
0.24584 | Enoch Burgess |  |  | Jordan Redden
0.27858 | Triniti Dickey |  |  | Jevon King
0.38074 | Angel Nolan |  |  | Leona Childress
0.80598 | Bruno Day |  |  | Uriah Rea
0.16983 | Enoch Faircloth |  |  | Jaime Boyle
0.96203 | Maximilian Ali |  |  | Andie Delaney
0.54901 | Blaise Leary |  |  | Caroline Corley
0.82878 | Deon Knoll |  |  | Tess Popp
0.56467 | Cailey Rubio |  |  | Davonte Sneed
0.20041 | Daijah Quezada |  |  | Bonnie Montes
0.43028 | Harley Butcher |  |  | Tayler Holm
0.27054 | Kathryn Maguire |  |  | Maximilian Devore
0.73136 | Chandler Adair |  |  | Ashley Morgan
0.34018 | Devin White |  |  | Chris Crandall
0.23409 | Vernon Pulido |  |  | Donald Holmes
0.96323 | Jewel Toney |  |  | Edward Ludwig
0.24055 | Quinton Miner |  |  | Will Benton
0.99741 | Areli Hofer |  |  | Tristen Suarez
0.39882 | Galilea Ha |  |  | Nicholas Campbell
0.28914 | Madisen Lackey |  |  | Alesha Delarosa
0.30472 | Yamile Herndon |  |  | Sean Roberts
0.57516 | Alexis Weber |  |  | Eliseo Shipley
0.79036 | Cale Mosier |  |  | Melvin Smart
0.49136 | Daryl Canady |  |  | Leigh Haggard
0.39515 | Anahi Menard |  |  | Jason Johnson
0.37536 | Frances Bayer |  |  | Carlton Bryant
0.43884 | Mariah Shoemaker |  |  | Demarco Malone
0.93659 | Jessie Samuels |  |  | John Cohen
0.23407 | Lazaro Montgomery |  |  | Robert Buck
0.64258 | Ismael Wallace |  |  | Trystan Chin
0.026539 | Lorraine Coker |  |  | Andrew Perry
0.85924 | Aubrie Atkins |  |  | Micah Noble
0.36952 | Annabel Jolly |  |  | Mariela Givens
0.36494 | Michael Sutter |  |  | Madisen Lackey
0.30752 | Rodney Ratliff |  |  | Hollie Bowen
0.12316 | Jerrod Patten |  |  | Jessika Rouse
0.86609 | Ivonne Rees |  |  | Ervin Moriarty
0.87723 | Simeon Hicks |  |  | Ismael Wallace
0.042246 | Trevin Durant |  |  | Veronica Mora
0.41372 | Immanuel Witt |  |  | India Thomas
0.89473 | Kaya Morton |  |  | Kaya Morton
0.98729 | Brianne Danner |  |  | Kaya Park
0.13185 | Eliseo Shipley |  |  | Estefania Bonds
0.73318 | Rory Rucker
0.8183 | Carlton Bryant
0.88334 | Julian Lawless
0.21153 | Caylin Way
0.24994 | Randall Hoy
0.44522 | Kenan Frank
0.0013306 | Marina Dobbins
0.79529 | Lina Lorenzo
0.44832 | Carolyn Bach
0.55191 | Britney McNeill
0.39017 | Karlie Bernal
0.75721 | Antwan Swisher
0.78654 | Mykayla Frame
0.10015 | Josue Barnett
0.016266 | Eleanor William
0.77825 | Milena Neil
0.84388 | Ty Mims
0.9967 | Bonnie Smalls
0.22234 | Reginald Sears
0.53566 | Cedrick Heard
0.051028 | Dwayne Henley
0.78568 | Rachel Coulter
0.3186 | Camryn Pimentel
0.91549 | Alec Tompkins
0.31189 | Uriel Godwin
0.11548 | Aman Lester
0.55163 | Erich Lindquist
0.50749 | Arden Guest
0.87564 | Cecelia Luce
0.036366 | Wade Barraza
0.37661 | Katheryn Salvador
0.80297 | Cristopher Dube
0.22785 | Quinn Goldstein
0.098136 | Annabel Winkler
0.04954 | Leigha Oakley
0.55584 | Jessika Rouse
0.30661 | Tristin Haag
0.28754 | Jaylene Duffy
0.49241 | Jalen Lea
0.28488 | Kenna Elam
0.038298 | Paola Hunt
0.62987 | Ulises Rapp
0.056089 | Laci White
0.60932 | Ashley Morgan
0.24851 | Daja Helms
0.67534 | Pamela Steele
0.70039 | Star Broderick
0.97853 | Kaylah Overton
0.68862 | Dyllan Ayers
0.55603 | Tahj Wynn
0.36044 | Fernando Peebles
0.38073 | Quentin Bernier
0.29289 | Asa Valencia
0.89886 | Alberto Alonso
0.48478 | Chase Montes
0.81305 | Trystan Chin
0.78783 | Octavio Barba
0.73718 | Janet Ali
0.37834 | Orion Seidel
0.058741 | Mohammad Lanning
0.58271 | Francisco Bone
0.3713 | Nathan Flanagan
0.90533 | Mireya Padilla
0.23601 | Trista Schaeffer
0.51236 | Kaylie Castro
0.63279 | Amaiya Kaufman
0.36998 | Spencer Suarez
0.10531 | Codey Bartholomew
0.47067 | Jazmyn Horvath
0.44767 | Ciana Dawson
0.70419 | Meredith Littleton
0.748 | Roman Santiago
0.46298 | Selina Reis
0.43735 | Keara Clifton
0.92341 | Vincent Pyle
0.082025 | Kaeli Prince
0.62451 | Ronnie Apodaca
0.98189 | Daisha Pagano
0.029716 | Roderick Sherrill
0.95209 | Deion Pate
0.94381 | Magdalena Smallwood
0.9694 | Nia Westbrook
0.10528 | Edward Ludwig
0.33928 | Ananda Villegas
0.90958 | Leigh Haggard
0.55063 | Julieta Herzog
0.34171 | Rhett Neumann
0.3639 | Aryanna Longo
0.60567 | Caroline Corley
0.35242 | Zayne Lackey
0.5683 | Andie Delaney
0.18179 | Linnea Weis
0.47669 | Hunter Lerma
0.28097 | Gaige Mcallister
0.11056 | Pamela Aquino
0.78061 | Kelsey Christiansen
0.25332 | Eli Hamby
0.48866 | Daija Beckman
0.12552 | Harrison Hennessy
0.26749 | Jerry Monson
0.44262 | Ty Hauser
0.4234 | Jordan Redden
0.17169 | Ivan Herron
0.47696 | Jaycie Pak
0.82639 | Victor Chiu
0.91666 | Gwyneth Hewitt
0.092643 | Alvin Matthews
0.95394 | Shana Logsdon
0.4253 | Dayne McDuffie
0.32021 | Micah Noble
0.28236 | Daryl Tirado
0.95813 | Vanesa Meeks
0.99365 | Deandre Pacheco
0.22626 | Holland Steffen
0.38061 | Will Benton
0.89221 | Tate Lo
0.88844 | Tionna Hooper
0.50486 | Hollie Bowen
0.44118 | Reuben Negron
0.91595 | Christion Mace
0.73365 | Dwight Aparicio
0.2089 | Jakob Thornton
0.047945 | Kaley Robinson
0.62712 | Demarco Malone
0.84567 | Donald Shaver
0.73055 | Averie Lemons
0.40952 | Draven Catalano
0.9431 | Kinsey Piazza
0.94496 | Grayson Yazzie
0.14762 | Chester Nugent
0.36771 | Alea Hubert
0.91984 | Maximilian Devore
0.31567 | Kamryn Aragon
0.65268 | Jevon Weller
0.50216 | Alexandra Perea
0.21197 | Sincere Stover
0.52103 | Armand Baxter
6.8654e-05 | Marquise Blalock
0.58123 | Hali Pierce
0.48033 | Darion Burnside
0.94895 | Reed Viera
0.81284 | Abby Branch
0.32939 | Trey Pemberton
0.6814 | Erin Rowe
0.41774 | Keven Conner
0.46328 | Riley Headley
0.14447 | Damien Best
0.036606 | Sammy Stewart
0.76907 | Nathanael Gay
0.43118 | Jackelyn Barragan
0.67869 | Jaylin Wiseman
0.33408 | Wilfredo Arsenault
0.060149 | Randall Acosta
0.084814 | Hasan Webber
0.4468 | Shayla Stokes
0.7875 | Liberty Drury
0.44624 | Miguel Avila
0.44744 | Ladarius Arteaga
0.077952 | Keyana Timmons
0.33284 | Treyton Mcnutt
0.51258 | Blake Mcnulty
0.63102 | Karla Baum
0.90344 | Kaiya Mott
0.72409 | Delanie Wise
0.55229 | Leigh Andrus
0.53726 | Raelyn Kline
0.90949 | Kylee Duenas
0.66655 | Yosef Gallant
0.72475 | Konnor Call
0.37159 | Johan Alves
0.50412 | Joy Kunz
0.11313 | Alejandro Henson
0.53739 | Kaya Park
0.94737 | Justice McCrary
0.93672 | Tonya Slade
0.403 | Asher Baron
0.87186 | Jailyn McClung
0.038829 | Osvaldo Allred
0.50935 | Abigayle Rhoades
0.094694 | Saira Whitt
0.15715 | Lorenzo Neal
0.30977 | Davonte Sneed
0.99873 | Reid Lance
0.55314 | Dyllan Page
0.12515 | Draven Keefer
0.74185 | Laci McCorkle
0.58466 | Chauncey Hollis
0.96268 | Neal Salisbury
0.040643 | Izaiah Briscoe
0.6161 | Jerod Mcghee
0.90506 | Rochelle Early
0.21977 | Carlie Curley
0.37156 | Kasey Graff
0.092293 | Elena Irby
0.84265 | Briana Rossi
0.7589 | Taylor Griggs
0.20953 | Jevon King
0.00037179 | Mercedes Bullard
0.11916 | Blaise Roland
0.0149 | Bryn Weems
0.10704 | Asa Winn
0.063745 | Luc Field
0.88089 | Deasia Keane
0.51432 | Sasha Cunningham
0.35796 | Karah Sweat
0.4776 | Melinda Metz
0.56359 | Sydney Madrigal
0.81591 | Notnamed Blue
0.83525 | Donavan Kuykendall
0.9513 | River Alicea
0.62998 | Susana Crider
0.036689 | Kami Gaffney
0.58591 | Yessenia Marks
0.51473 | Tayla Lange
0.089171 | Enzo Elliott
0.9634 | Kai Humphrey
0.98569 | Rosalinda Kwon
0.90787 | Alex Moya
0.1473 | Alaina Schmid
0.70381 | Troy Voss
0.902 | Slade Mock
0.84729 | Jaydon Ray
0.94357 | Maverick Brooks
0.79856 | Johnathon Seward
0.25968 | Darrian Joyce
0.56245 | Lawrence Mora
0.58804 | Shakayla Russ
0.068388 | Lukas Littleton
0.34428 | Hillary Merritt
0.40329 | Chris Crandall
0.08976 | Saul Puckett
0.82074 | Abraham Parish
0.67718 | Kelis Gall
0.092581 | Yvonne Dominguez
0.122 | Arnold Chen
0.74616 | Edna Wisniewski
0.96039 | Alton Sales
0.26579 | Garret Engel
0.95659 | Patience Edmondson
0.25549 | Brendan Moriarty
0.1181 | Korbin Ricks
0.96579 | Natasha Asher
0.67566 | Alesha Delarosa
0.04743 | Maeve Andrade
0.44215 | Estefania Bonds
0.24871 | Diamond Stump
0.57741 | Christopher Keck
0.11517 | Alonso Bradley
0.55028 | Christina Maldonado
0.57319 | Kendall Myrick
0.72033 | Maximiliano Childress
0.60274 | Bronson Stubbs
0.17716 | Ayana Poston
0.48451 | Dashaun Alexander
0.48112 | Brea Graves
0.45041 | Miguel Tolbert
0.66453 | Melvin Smart
0.68929 | Roxanne Whitcomb
0.12977 | Jania Brinson
0.68702 | Melvin London
0.6418 | Giancarlo Kilgore
0.25214 | Ronaldo Mitchell
0.81023 | Ruth Trinidad
0.89189 | Tayler Holm
0.41253 | Morgan Dupont
0.35572 | Rhys Wharton
0.18705 | Tess Popp
0.29457 | Alani Knapp
0.80167 | Trinity Paredes
0.77413 | Stephon Houser
0.84086 | Jaron Horton
0.31142 | Harrison Mize
0.97929 | Malika Medina
0.25749 | Bradley Woodall
0.7772 | Alyssa Rocha
0.1671 | Katrina Bragg
0.67707 | Joshua Malley
0.72322 | Marques Rossi
0.84536 | Alexzander Lo
0.80007 | Jordyn Montano
0.49668 | Kahlil Fink
0.46845 | Cortney Cheung
0.18126 | Kaitlyn Herron
0.45715 | Dominick Conn
0.20131 | Jacquez Temple
0.061446 | Jaime Mace
0.62383 | Alec Gay
0.2172 | Kathrine Root
0.40046 | Enrique Cheng
0.88433 | Aleah Hawkins
0.73624 | Katlynn Daly
0.73876 | Bianca Schulze
0.5857 | Marian Hedges
0.74553 | Uriah Rea
0.14849 | Darian Canfield
0.69747 | Lamont Nadeau
0.78676 | Jack London
0.96205 | Tavion Benedict
0.097464 | Kristopher Hutcheson
0.743 | Analise McIntosh
0.82622 | Kenia Myles
0.83806 | Isai Frank
0.44896 | Kaylee Schubert
0.30714 | Camille Thorpe
0.65313 | Jameson Brackett
0.40394 | Curtis Polanco
0.11042 | Hanna Stein
0.33828 | Agustin Webster
0.96584 | Aaliyah Bentley
0.47661 | Alden Noll
0.49443 | Dillon Justice
0.80199 | Mariela Givens
0.26229 | Varun Kumar
0.53809 | Sage Reiter
0.17622 | Deon Abel
0.9992 | Codey Nieto
0.43538 | Braydon Lemke
0.20924 | Howard Zhang
0.19494 | Lillie Ashworth
0.49566 | Jaya Denson
0.26824 | Johnson Mai
0.10082 | Cordell Temple
0.58391 | Abraham Tanner
0.66662 | Hope Richards
0.86216 | Zaire Merchant
0.85744 | Jamia Jefferson
0.13099 | Dwayne Mason
0.3626 | Cade Denny
0.20469 | Jaime Boyle
0.78416 | Jameson Eckert
0.53651 | Devan Hamilton
0.67118 | Geovanni Mullis
0.60501 | Bailey Kilpatrick
0.91427 | Hanna Bloom
0.030378 | Javion Hulsey

## 1c Final interview list
Sampling tool – final interview list
Copy the names from Column E in Tab 1b, and Paste special -> Values only here on this page. This is your final interview list for your sample, generated randomly on the previous page. Once you create your final list of randomly selected names, it is important that that list does not change. It includes a few extra names (15 per cent extra) to account for any last-minute unavailability. This list becomes your guide for creating your interview plan.
Aidan Eubanks
Jailyn McClung
Arnold Chen
Mr. Kevin Nelson
Alexis Weber
Quinton Miner
Alani Knapp
Laci White
Victor Chiu
Jerry Monson
Asa Winn
Yaritza Tobin
Dwight Daily
Roxanne Whitcomb
Jaylen McCullough
Jamie Morrison
Michael Cruz
Francis Centeno
Mark Glass
Shakayla Russ
Keyshawn Kirkpatrick
Hali Pierce
Angela Cook
Varun Kumar
Octavio Barba
Devlin Waugh
Kory Quiroz
Ciara Sutter
Eli Hamby
Kaeli Prince
Chandler Adair
Tyreese Fullerton
Randall Hoy
Paola Hunt
Lisa George
Angel Nolan
Magdalena Smallwood
Mr. Kyle Dougherty
Michael Sutter
Roman Santiago
Deon Knoll
Garret Engel
Lorenzo Neal
Andrea Carter
Breanna Flores
Areli Hofer
David Garcia
Carolyn Bach
Katlynn Daly
Michael Evans
Camille Singleton
Amaiya Kaufman
Mohammad Lanning
Eric Wilson DDS
Mariah Shoemaker
Ulises Rapp
Pamela Steele
Tonya Slade
Antoine McCauley
Patience Roach
Raelyn Kline
Reed Viera
Erich Delagarza
Briana Rossi
Tahj Wynn
Liberty Drury
Lisa Davis
Ashlin Lozano
Leona Childress
Morgan Dupont
Kahlil Fink
Riley Headley
Sidney Franklin
Madison Walker
Cristopher Dube
Reginald Sears
Caroline Corley
Taylor Griggs
Paula Adams
Stephen Merritt
Carleigh Marcus
Kaya Park
Jaron Horton
Camille Thorpe
Jorden Cantrell
Hunter Lerma
Grayson Yazzie
Heather Alexander
Kaya Morton
Tate Lo
Tess Popp
Christina Cabrera
Chauncey Hollis
Julieta Herzog
Jackelyn Barragan
Rodney Ratliff
Britney McNeill
Notnamed Blue
Trey Pemberton
Jerod Mcghee
Barry Ricker
Troy Voss
Andie Delaney
Octavio Riggins
Kathrine Root
Larry Terrell
Donald Shaver
Nicholas Campbell
Draven Catalano
Darlene Davis
Patrick Jefferson
Yessenia Marks
Ryan Henry
Courtney Seeley
Kaylah Overton
Ashley Morgan
Claire Herron
Ronaldo Mitchell
Eleanor William
Ayla Petrie
Devin White
Chester Nugent
Bradley Woodall
Kenan Frank
Amy Barnes
Annabel Jolly
Robert Buck
Keara Clifton
Mercedes Bullard
Mary James
Hamza Yates
Abraham Parish
Joy Fernandes
Dyllan Ayers
Anna Kennedy
Yvonne Dominguez
Talon Gray
Luc Field
Sylvia Garcia
Codey Bartholomew
Alexzander Lo
Will Benton
Coleton Zielinski
Alaina Schmid
Zaire Landers
Jamir Mayhew
Margo Mueller
Jamie Ellison
Danica Murillo
Tyler Smith
Tayler Holm
Veronica Mora
Sage Reiter
Aaliyah Bentley
Justice McCrary
Chase Gage
Arthur Mitchell
Davonte Sneed
Brooke Garcia
Sasha Cunningham
Alyssa Rocha
Edna Wisniewski
Enoch Burgess
Lawrence Mora
Blaise Roland
Bailey Cordero
Patience Edmondson
Ivonne Rees
Tavian Yazzie
John Cohen
Ms. Elizabeth Kim
Camryn Pimentel
Kendall Myrick
Asa Valencia
Joseluis Flanders
Harley Butcher
Jaylin Wiseman
Mykayla Frame
Luke Carrier
Curtis Polanco
Lamont Nadeau
Ariana Love
Zayne Lackey
Karla Baum
Alesha Delarosa
Emanuel Colby
Kristopher Hutcheson
Marcellus Halstead
Beatrice Christiansen
Jaime Mace
Kenna Elam
Marquise Blalock
Shaina McCann
Madison Schumacher
Francisco Bone
Alex Moya
Raekwon McLean
Shana Logsdon
Reilly Kinney
Jalen Quick
Stevie Sutherland
Kathryn Maguire
John Wilson
Rory Rucker
Cindy Carter
Lillie Ashworth
Darion Burnside
Cecelia Luce
Daijah Quezada
Cedrick Elam
Heather Huffman
Cale Felder
Erich Lindquist
Craig Dion
Natasha Asher
William Bennett
Simeon Hicks
Elena Irby
Dyllan Page
Ronnie Apodaca
Darian Canfield
Deandre Pacheco
Jaylene Duffy
Cristofer DeJesus
Leigh Andrus
Dwight Aparicio
Guadalupe Kurtz
Bryn Weems
Osvaldo Allred
Deion Pate
Ty Hauser
Dwayne Henley
Alesha Freedman
Tayla Coronado
Micah Noble
Christopher Adams
Jamia Jefferson
Javion Hulsey
Howard Zhang
Devan Hamilton
Kimberlee Mitchell
Daja Helms
Nathanael Gay
Keyana Timmons
Sunny Agee
Jacquez Temple
Hanna Stein
Brianne Danner
Abigayle Rhoades
Mark Lawrence
Ismael Nielson
Konnor Call
Holland Steffen
Cindy Harrison
Alea Hubert
Trista Schaeffer
Ivan Herron
Melvin London
Trey Dominguez
Harley Briggs
Averie Lemons
Selina Reis
Jakob Thornton
Ellis Downing
Saira Whitt
Aman Lester
Rochelle Early
Reuben Negron
Eliseo Shipley
Spencer Suarez
Katheryn Salvador

## 2 Budget
Budget
Use this template to map out the costs for your Light Wheel survey. You can use the project plan and your responses from the data-collection plan to inform your budget.
What is your total survey budget available?______________
Cost area | No. of units | Unit measure | Unit cost | Total cost | Notes
Data collector/staff |  |  |  | 0
Travel |  |  |  | 0
Accommodation/venue |  |  |  | 0
Food/drink |  |  |  | 0
Printing/resources (eg pens, clipboards)
Translation
Mobile phones or tablets
Airtime/mobile data |  |  |  | 0
Incentives |  |  |  | 0
Reporting (eg visual products, feedback to communities)
TOTAL COST |  |  |  | 0

## 3 Data-collection deci
Data-collection decisions
Use this template to consider key decisions that you need to make as you form your data-collection plan. This will inform your daily survey schedule and your overall survey project plan, and will have implications for your survey budget.
Key decision-making questions | Decision points | Your data-collection decisions
Where will you do your interviews? | Will you conduct interviews at a central location, at people's homes, by phone, or another location?
How many interviews will your data collectors do per day? (on average) | How many hours per day will your data collectors be interviewing?
How many interviews do you expect a data collector to complete each day?
How many male and female data collectors do you have? | How many male data collectors will you have on your team?
How many female data collectors will you have on your team?
Will they work alone or in pairs?
Will male data collectors interview female respondents?
Will female data collectors interview male respondents?
When do your interviews need to be completed by? | What date do your interviews need to be completed by?
Will you give incentives? | Will you give incentives to respondents?
Please explain:
On the next page 'Project plan', you can create a schedule for each survey site, listing who will be interviewed on each day.

## 4 Project plan
Project plan
Think through your project plan below, filling in realistic dates and any notes that will help you plan your survey timeline:
Activity | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8
Planning
Training
Piloting
Implementing
Analysis | [7 empty] | ➔
Debrief
Reporting | [7 empty] | ➔
On the next page 'Daily schedule', you can create a schedule for each survey site, listing who will be interviewed on each day.
Planning | This might take anything from a few days up to a couple of weeks, depending on the scale and scope of the survey, and who is involved.
Training | You’ll need to train each of your data collectors on using the survey, the methodology you’re using in your survey, and what the daily data-collection plan looks like.
Pilot testing | You’ll usually plan an opportunity for data collectors to go out and do a test-run of data collection in the community. This will allow them to make mistakes and ask questions.
Implementing | This is when you actually go and do the survey! It depends on how many surveys you’re doing, and how many data collectors are on your team – but this could take anywhere from one week to one month depending on your methodology and plan.
Analysis | After the surveys are all done, you’ll then spend time analysing the results and cleaning up any mistakes. This can take a bit of time to work through. See Part 4: Analyse in the Light Wheel toolkit (available at learn.tearfund.org/LW4) for more guidance.
Debrief | As soon as you can after the survey implementation is done, gather all the data collectors, and do a debrief focused on what went well, what went wrong, and what they would change next time.
Reporting | Once the analysis and debrief are done, gather all the data together, presenting it in a report and summary report, for example. However you choose to communicate your findings, make sure you share them with the key stakeholders, such as the survey respondents, community leaders, project staff and donors (all those whom you have permission to share information with). See Part 5: Communicate in the Light Wheel toolkit (available at learn.tearfund.org/LW5) for more guidance on sharing your findings in different ways.
Note on B21: HELEN to add hyperlink to *Part 4: Analyse* - to Part 4 page on Tearfund Learn -Sarah La Trobe learn.tearfund.org/LW4 -Sara Baines
Note on B23: HELEN to add hyperlink to *Part 5: Communicate* - to Part 5 page on Tearfund Learn -Sarah La Trobe learn.tearfund.org/LW5 -Sara Baines

## 5 Daily schedule
Daily schedule
Now that you have your random sample and have started to think through your data-collection plan, you can begin to develop a schedule for the interviews you want to conduct. Use this template to fill in realistic dates, locations for each day, data collector names and interviewee names.
This table is for 48 names. Create more columns and rows for additional interviewee names and additional data collector teams.
Data collectors | [Date 1]: [Location 1] |  | [Date 2]: [Location 2] |  | [Date 3]: [Location 3]
| AM | PM | AM | PM | AM | PM
Team 1: [Name of data collector 1] [Name of data collector 2] | [Interviewee name] | [Interviewee name] | [Interviewee name] | [Interviewee name] | [Interviewee name] | [Interviewee name]
| [Interviewee name] | [Interviewee name] | [Interviewee name] | [Interviewee name] | [Interviewee name] | [Interviewee name]
| [Interviewee name] | [Interviewee name] | [Interviewee name] | [Interviewee name] | [Interviewee name] | [Interviewee name]
| [Interviewee name] | [Interviewee name] | [Interviewee name] | [Interviewee name] | [Interviewee name] | [Interviewee name]
Team 2: [Name of data collector 1] [Name of data collector 2] | [Interviewee name] | [Interviewee name] | [Interviewee name] | [Interviewee name] | [Interviewee name] | [Interviewee name]
| [Interviewee name] | [Interviewee name] | [Interviewee name] | [Interviewee name] | [Interviewee name] | [Interviewee name]
| [Interviewee name] | [Interviewee name] | [Interviewee name] | [Interviewee name] | [Interviewee name] | [Interviewee name]
| [Interviewee name] | [Interviewee name] | [Interviewee name] | [Interviewee name] | [Interviewee name] | [Interviewee name]
Contact respondents prior to interview
Will you contact respondents prior to interview? | Yes/No
How will you contact them? | Phone/in-person/email/other
When will you contact them? | 1 month before/1 week before/2 days before/other
On the 'Budget' tab you can use this project plan to develop a budget and estimate the costs of your survey.