## Slide 1
ROOTS 1+2
Advocacy toolkit
www.tearfund.org/advocacy_toolkit

## Slide 2: Section H Advocacy Cycle Stage 5 Monitoring, reviewing, evaluation and learning

## Slide 3: Section H: Monitoring, reviewing, evaluation
 | Monitoring | Reviewing | Evaluation
When? | continuously | regularly | occasionally
What? | efficiency | effectiveness, relevance, immediate impact | longer-term impact, sustainability
Who is involved? | communities, staff, allies | communities, staff, allies | communities, staff, allies, opponents, targets
Evidence? | internal | internal & external | internal & external
Who is it for? | communities, staff | communities, staff, allies, donors | communities, staff, allies, donors, other NGOs
Why? | confirm or make minor changes in project design | confirm project design, make minor changes in plan | inform major changes in plan, apply learning to future similar projects

## Slide 4: Section H: Why bother with monitoring, reviewing and evaluation?
Accountability - to people in the affected communities - to allies and others in advocacy coalitions - to targets and decision-makers - to donors
Learning
Demonstration of impact (& evidence in support)
Participation from all stakeholders

## Slide 5: Section H: The importance of learning
Understand what worked or did not work – when, where, with whom, under what circumstances and why
Identify success – to help others improve
Identify failure – to help others avoid similar mistakes
Allow sufficient time to reflect on what has happened and what is happening
Make specific recommendations to ensure progress

## Slide 6: Section H: How to monitor and review advocacy
Gather data that is useful and relevant
Balance between quantitative and qualitative data
‘Not everything that counts can be counted. And not everything that can be counted, counts’
Consult different people and get different perspectives
Identify lessons learnt

## Slide 7: Section H: How to monitor and review advocacy
Have we done what we said we would do, when we said we would do it?
How well have we done what we said we would do?
Where have we done well? What can we improve further?
Where have we not done well? Why is this and what can we learn?
What needs to be changed in order to get our plan back on track, and how are we going to do this?

## Slide 8: Section H: How to evaluate advocacy
Be participatory
Assess impact
Gather evidence of change
Be objective
Identify lessons learnt

## Slide 9: Section H: How to evaluate advocacy
Why is an evaluation needed?
What do we want the evaluation to achieve?
What are the central questions that the evaluation must address?
What specific areas do we want the evaluation to address?
What approaches and techniques would we prefer the evaluator to use?
What logistics do we need to consider?